## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone: Acquire required tablets (Sourcing)
Select vendor for tablet |  |  |  | 2
Identify vendor for card processing |  |  |  | 2
Select tablet model |  |  |  | 2
Signing contract and agreement |  |  |  | 2
Tablet shipping | Shipping deplayed by 4 days, hence the original estimate has been updated to Confirm number of devices |  |  | 11
Milestone: Tablet design
Marketing team to select Tablet layout and branding |  |  |  | 3
Revamp Menu |  |  |  | 5
Tablet menu and Coupon |  |  |  | 2
Prepare mock-ups |  |  |  | 1
Add-on for multi-language support |  |  |  | 1
Add-on for tablet games, news |  |  |  | 1
Install post-dining survey |  |  |  | 1
Milestone: Tablet installation
Electrician for wiring the tablets | Attempted wiring through tables at lease once Notify GMs when their locations need to close for wiring Check with electrician on whether mornings or afternoons work better with their schedule |  |  | 4
Hardware installation for tablets |  |  |  | 2
Tablet install to the bar area |  |  |  | 1
Tablet software synch-up | Never attempted this before |  |  | 3
Milestone: Tablet features testing
Test tablets for working |  |  |  | 7
Test run table top ordering |  |  |  | 3
Milestone: Training for staff
Training plan for the staff |  |  |  | 3
Training material for tablet usage and integration |  |  |  | 2
GM to address staff about tip changes |  |  |  | 1
Pre-training meeting |  |  |  | 1
Training for Managers | Attempted the staff training regularly |  |  | 1
Staff to train rest of management, FOH staff, BOH staff | Never attempted this before |  |  | 2
Test run the tablet ordering before launch |  |  |  | 1
Update menu via software | Never attempted this before |  |  | 1
Create a Troubleshooting plan |  |  |  | 1
Prepare for Launch day |  |  |  | 2

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Sourcing
Select vendor for tablet
Identify vendor for card processing
Select tablet model
Signing contract and agreement
Tablet shipping | Shipping deplayed by 4 days, hence the original estimate has been updated to Confirm number of devices | 11 | 7 | 10 | 15
Milestone: Acquire required tablets
Design
Marketing team to select Tablet layout and branding
Revamp Menu |  |  | 3 |  | 21
Tablet menu and Coupon
Prepare mock-ups |  |  | 1 | 2
Add-on for multi-language support
Add-on for tablet games, news
Install post-dining survey
Milestone: Complete tablet design
Installation
Electrician for wiring the tablets | Attempted wiring through tables at lease once Notify GMs when their locations need to close for wiring Check with electrician on whether mornings or afternoons work better with their schedule |  | 2 |  | 4 | M
Hardware installation for tablets
Tablet install to the bar area
Tablet software synch-up | Never attempted this before | 3 | 1 | 2 | 11 | L
Milestone: Complete tablet installation
Testing
Test tablets for working
Test run table top ordering
Milestone: Complete tablet features testing
Training
Training plan for the staff
Training material for tablet usage and integration
GM to address staff about tip changes
Pre-training meeting |  |  | 0.25
Training for Managers | Attempted the staff training regularly |  | 0.5 |  |  | L
Staff to train rest of management, FOH staff, BOH staff | Never attempted this before |  | 1 |  |  | H
Test run the tablet ordering before launch
Update menu via software | Never attempted this before |  |  |  |  | L
Create a Troubleshooting plan
Milestone: Complete training for staff
Launch day

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Multi-language support | https://restauranttechnologynews.com/2020/01/4-technology-must-haves-to-improve-your-restaurant-business/ | 2022-05-25 | Small add-on provides menu and service in preferred language. This makes customers to feel at home
Customer engagement | https://www.restaurantdive.com/news/tabletop-tech-speeds-up-service-and-boosts-profits-study-says/560152/ | 2022-05-25 | Customers especially kids can be engaged by allowing games & news with minimal add-ons to tablet. It increases their intrest as well

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Faster, more effecient experience (Average ticket time) | 8 minutes for appetizers | How was the dinning experience? Did the food arrive in expected time? | How long did the customers wait for appetizers? | FALSE
Faster, more effecient experience (Average ticket time) | 12-15 minutes for entrees | How was the dinning experience? Did the food arrive in expected time? | How long did the customers wait for entrees? | FALSE
Customer satisfaction | 1 minute check-out time | How was the customer check-out experience? Were any issues identified during the check-out? | How much time it took to complete the payment process? | FALSE
Tablet | Less than 5% of customers report issue each week | Were any issues reported with tablet usage? How was th ease of use? | How many issues were found in tablet report? | FALSE
Cutting down incorrect orders | 98% of order accuracy | Did the correct order arrive? Were there any changed made to the order? | How accurate the ordered food matched the served? | FALSE
Customer satisfaction | Wait time of 10 minutes or less | Were customers available in lobby during the wait time? Were the customers provided table in right time? | How much was the average wait time? | FALSE
Customer satisfaction | Increase customer retention in tablet areas by 5% | How is the tablet area populated in the bar? Were customers willing to use tablets over servers? | How many repeat customers occur in a month? | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
8 minutes for appetizers | How was the dinning experience? Did the food arrive in expected time? | How long did the customers wait for appetizers? | Rate your overall dinning experience on the scale of 5. 1 being poor and 5 being excellent | Scaled | 1: Poor | 2: Average | 3: Good | 4: Very Good | 5: Excellent
12-15 minutes for entrees | How was the dinning experience? Did the food arrive in expected time? | How long did the customers wait for entrees? | What was the average wait time for the entrees you ordered? | Multiple choice | 1: Less than 10 minutes | 2: 12 - 15 minutes | 3: 15 - 30 minutes | 4: More than 30 minutes
1 minute check-out time | How was the customer check-out experience? Were any issues identified during the check-out? | How much time it took to complete the payment process? | Rate your check-out processing in terms of time taken on a scale of 5. 1 being poor and 5 being excellent? | Scaled | 1: Poor | 2: Average | 3: Good | 4: Very Good | 5: Excellent
Less than 5% of customers report issue each week | Were any issues reported with tablet usage? How was th ease of use? | How many issues were found in tablet report? | Were there any issues identified during the tablet usage? | Open-ended | Open-ended
98% of order accuracy | Did the correct order arrive? Were there any changed made to the order? | How accurate the ordered food matched the served? | Did the served food match your order? | True/False | 1: True | 2: False
Wait time of 10 minutes or less | Were customers available in lobby during the wait time? Were the customers provided table in right time? | How much was the average wait time? | What was the wait time in lobby? | Multiple choice | 1: Less than 5 minutes | 2: 5 to 10 minutes | 3: 15 to 30 minutes | 4: More than 30 minutes
Increase customer retention in tablet areas by 5% | How is the tablet area populated in the bar? Were customers willing to use tablets over servers? | How many repeat customers occur in a month? | Will you recommend this to your friend? | Yes/No | 1: Yes | 2: No
|  |  | Do you prefer table top tablet over a server? | Yes/No | 1: Yes | 2: No